

	
[image: image1.wmf]
	UNITED NATIONS

ECONOMIC COMMISSION FOR AFRICA

	
	


	AFREF PROJECT Proposal – Summary 

	Title:
	Implementation of the African Reference Frame (AFREF)

	Implementing Agencies:
	Economic Commission for Africa

	Major Partners:
	Regional Centre for Mapping of Resources for Development (RCMRD)
Regional Centre for Training in Aerospace Surveys (RECTAS)
African Organisation for Cartography and Remote Sensing (AOCRS)
International Association of Geodesy (IAG)
International GNSS Service (IGS)
National Mapping Organizations

	Development Sectors:
	Surveying and Mapping
Infrastructure Development
Science and Technology

	Execution Period:
	24 months

	Estimated Cost:
	$1,001,000


Implementation of the African Reference Frame (AFREF) – Project Proposal
The AFREF Concept

The African Geodetic Reference Frame (AFREF) was conceived as a unified geodetic reference frame for Africa, fully consistent and homogeneous with the International Terrestrial Reference Frame (ITRF), which will be the fundamental basis for the national and regional three-dimensional reference networks. The reference frame will be composed of a network of points where precise observations will be taken and used to define a Terrestrial Reference Frame that will result in a best-fit datum over Africa. The network would be at such a density that positioning professionals (surveyors, engineers, environmentalists, agriculturalists, mineral prospectors, etc) would always be within a reasonable distance of at least one such control point any place in Africa, with relevant parameters made freely available to practitioners. 

AFREF will be based on current satellite positioning technologies, and will form the geodetic infrastructure for multinational projects requiring precise geo-referencing (e.g. three-dimensional and time dependent positioning, geodynamics, precise navigation, and geo-information). Like other continental geodetic reference frames, it will be part of the global geodetic infrastructure. As such, it is being implemented and will be maintained in close cooperation with international partners with expertise and interest in geodetic reference frames, notably the International Association of Geodesy (IAG), the International GNSS Service (IGS), the United Nations Office for Outer Space Affairs (UNOOSA), among others.

Justification and Rationale

Service delivery to people, households and businesses – land allocation and development permits, water connections, waste management, electricity and transportation, schooling and health provision, accessible markets, and security – requires linking places where people live and/or transact business and the conditions that subsist there with access to resources and the services they need. Therefore, all development projects, applications, services and products need to be geo-referencing. Such geo-referencing require uniform coordinate systems defined by the geodetic reference frame. 

So far, each African country has its national geodetic reference frame for producing maps and other geoinformation products. These reference systems are usually based on local origins or datums, which restrict their use to particular countries and make it difficult to accurately represent cross-border features on (sub) regional maps. For example, roads, watershed and ecosystem boundaries and wildlife reserves do not necessarily stop at national borders and may appear disconnected when national maps are joined together for regional planning and decision analysis. Work on transnational infrastructure projects is normally undertaken in sections and a uniform mapping surface is required to ensure that the sections actually join up. 

[image: image2.jpg]Team Work





Figure 1 Oh S#%t!

All African countries have embraced Global Navigation Satellite System (GNSS) technologies, particularly Global Positioning system (GPS), in the various geo-information applications, services and products. GPS positions are defined in the datum of the World Geodetic System of 1984 (WGS-84). This datum is also used for several international applications that Africa participates in. For instance, the International Civil Aviation Organization (ICAO) has adopted WGS84 as the system for specifying the absolute geographic coordinates of Aerodrome Reference Points (ARP), various airport facilities and radio navigational aids. Yet these same features need to be shown with other features on cadastral and topographic maps for national and local planning and service delivery. With the increasing use and application of GNSS, there is an urgent need to establish and determine the transformation parameters to relate positions derived with GNSS technologies in the global reference frame to other features in appropriate national mapping systems. By determining the translation parameters between the current existing traditional national reference frame or frames, all legacy geospatial data and information based on traditional reference frames will not be lost or discarded.  This implies determining the parameters for the best-fitting datum for Africa and establishing a network of points to realize the associated terrestrial reference frame – the twin objectives of the AFREF project. 

Project Objectives

The main objective of the project is to coordinate ongoing and new activities aimed at computing the parameters of an African Geocentric Datum, and implementing and maintaining the AFREF network of points described above and making relevant data freely available to users. In the first instance, it is aimed that there should be at least one IGS station in every country. When completed, it is envisaged that users will not be more than 1000 Km from one such point any place in Africa, to be eventually densified to reduce that distance to 500Km or less. Emphasis will be on developing and maintaining guidelines for reference stations and peripheral components and protocols for data collection and management; and strengthening the management structure and coordinating several relevant initiatives to increase the pool of stations available for positioning and other scientific uses.

The formal objectives of AFREF are to:

· define the continental reference system of Africa. Establish and maintain a unified geodetic reference network as the fundamental basis for the national 3-d reference networks fully consistent and homogeneous with the global reference frame of the ITRF;

· realize a unified vertical datum and support efforts to establish a precise African geoid, in concert with the African Geoid project activities;

· establish continuous, permanent GNSS stations such that each nation or each user has free access to, and is, at most, 1000km from such stations;

· determine the relationship between the existing national reference frame or frames and the ITRF to preserve the legacy geospatial data and information based on the existing reference frame:

· provide a sustainable development environment for technology transfer, so that these activities will enhance the national networks, and numerous applications, with readily available technology; and

· assist in establishing in-country expertise for the implementation, operation, processing and analysis of modern geodetic techniques, primarily GNSS.

On-Going Activities

This proposal is not for an entirely new project, but a revamp of an on-going initiative. The concept of a unified reference frame for Africa has been recognized since the 1980s and the African Doppler Survey (ADOS) project was intended to provide it. The ADOS project ended in 1986 without fully achieving its objectives, mainly because the difficulty in satisfying the simultaneous observations required by the Doppler Satellite technology used at the time. 

However, the concept of a unified reference frame for Africa was kept alive, mainly by the International Association of Geodesy (IAG) and the United Nations Office for Outer Space Affairs (UNOOSA). This was discussed in 2000 during the meeting of the Global Spatial Data Infrastructure (GSDI) in Cape Town. The African Organization for Cartography and Remote Sensing (AOCRS) conducted several workshops and meetings on the establishment of a North African Reference Frame (NAFREF). In 2002, one of a series of workshops on the use of GNSS technology organized by UNOOSA and the government of the United States of America was held in Lusaka, Zambia for Africa. This workshop further highlighted the need for an African Reference Frame (AFREF) and the feasibility of its establishment with GNSS technology. The workshop recommended that an African institution with appropriate geoinformation mandate should take the lead in coordinating the project, which has hitherto been driven by the IAG and UNOOSA. 

Before this time, in 2001, the United Nations Committee on the Peaceful Uses of Outer Space (COPUOS) had established an Action Team on Global Navigation Satellite Systems (GNSS) to carry out actions to improve the efficiency and security of transport, search and rescue, geodesy and other activities by promoting the enhancement of, universal access to and compatibility of, space-based navigation and positioning systems. The Action Team on GNSS (38 member States and 15 inter-governmental and non-governmental organizations) recommended that an International Committee on GNSS (ICG) should be established to promote the use of GNSS infrastructure on a global basis and to facilitate exchange of information. This ICG finally became operational in 2006.

Following on the 2002 Lusaka workshop, the Regional Centre for Mapping of Resources for Development (RCMRD), during the Conference of Ministers of its contracting members in Windhoek, Namibia, convened a preparatory workshop to define a uniform and modern coordinate reference system for the continent. The workshop participants started by reviewing past efforts to establish a unified Geodetic Datum for Africa along with a discussion of the status of various geodetic projects in some countries in Africa. The outcome of the workshop was a declarative document called “Windhoek Declaration on an African Reference Frame,” which outlined the concepts and principles of a native geodetic coordinate reference for Africa (the AFREF Project). 

The Steering Committee

The Windhoek Declaration, together with the recommendation from the UNOOSA/USA Lusaka workshop, was in 2003 submitted to the third session of the Subcommittee on Geoinformation of the Committee on Development Information (CODI-Geo) as the forum where heads of national mapping agencies meet for adoption. CODI-Geo adopted the two documents and set up a Working Group. The members of this working group are: 
1. Regional Centre for Mapping of Resources for Development (RCMRD), represented by the Director General, Co-Chair;
2. African Organisation of Cartography and Remote Sensing (AOCRS), represented by the Secretary General, Co-Chair;
3. Regional Centre For Training In Aerospace Surveys (RECTAS), the Executive Director;
4. Representative of the North African (sub) Reference Frame (NAFREF): Tunisia, Head of National Surveys & Mapping Organisation;
5. East African Reference Frame (EAFREF), represented by Tanzania, Director of Surveys & Mapping;
6. West African Reference Frame (WAFREF), represented by Nigeria, Surveyor General of the Federation; 
7. Southern African Reference Frame (SAFREF), represented by Namibia, Director of Surveys & Mapping;
8. Central African Reference Frame (CAFREF), represented by Congo Republic, Directeur, Centre de Recherche Géographique et du Production Cartographique. 
This working group plus the Chair of the International Association of Geodesy, sub commission on Reference Frames, Africa (SC 1.3d), constitutes the International Steering Committee on AFREF (ISCA). 

Current Status

A sparse continuous operating reference stations (CORS) GNSS network has been established and managed by some member States, IGS and other partners. This network includes at least one station in the following countries: Algeria, Egypt, Mozambique, Ghana, Kenya, Benin, Morocco, South Africa, Namibia, Zambia, Côte d’Ivoire, Uganda and Nigeria. Other countries are expected to establish CORS soon. These are Malawi, Angola, Mauritius, Cameroon and Nigeria. Some data from the established CORS is already being received by the Hartebeesthoek Radio Astronomy Observatory (HartRAO) data Centre in South Africa and the International GNSS Service (IGS). 

While the Windhoek Declaration envisages that the stations would be owned and managed by national authorities responsible for geodesy, it recognized that some countries might need various forms of assistance to install and/or operate the stations. A call for participation (CfP) was therefore prepared and distributed inviting organizations to indicate what support they could provide to the AFREF project. The call was sent to a broad range of organizations, including National Mapping Organizations, Universities, research organizations, GNSS hardware and software vendors and donor community. 

In response to the CfP and contacts by members of the International Steering Committee, Leica and Trimble have donated three and five reference stations respectively. Each Leica system consists of a Leica GRX1200 Pro GG receiver, a Leica AT504 GG Choke Ring antenna and the Leica GPS Spider Software and Site Server as well as the Leica GNSS QC Software for permanent quality control and data analysis. Two Leica receivers have been installed at RCMRD and the Regional Centre for Training in Aerospace Surveys (RECTAS), while the third will be installed in Ghana. Each Trimble system consists of a Trimble® NetR5™ reference station with Zephyr™ Geodetic II antenna and Trimble® Integrity Manager™ software license; real-time and post processing modules, supporting 10 reference stations. Two of these will be installed at the premises of the ECA Sub Regional Offices in Niger and Cameroon, the third will be installed in Botswana and the location of the remaining two will be determined by the International Steering Committee.

Multi-disciplinary Aspects of GNSS in Africa

Global Navigation Satellite Systems (GNSS) were first introduced in the late 1960’s primarily for navigation purposes. As the name of the first such system implies, notably the United States Navy Navigation Satellite System (US NNSS), the system was primarily for military navigation applications. Since then, GNSS has developed to become widely used by civilian users and scientists not only for navigation purposes but also for a wide variety of non-navigation applications such as geodesy, surveying, geophysics, meteorology, geohydrology, space weather, timing and disaster mitigation and monitoring. Although AFREF was originally established as a geodetic project, numerous non-geodetic organizations have installed GNSS equipment throughout Africa to serve their own observation needs for scientific and development purposes, resulting in duplication of effort and resources. The map in Fig 2 shows the positions of some of the known or planned installations of GNSS equipment as at September 2007, not all of which are purely for geodetic applications. On the map, red dots indicate established stations and blue dots indicate planned stations.  However, the information shown thereon is not to be regarded as definitive but merely as an indication of the increased density of permanent GNNS base stations. For clarity only a representative sample of installed stations have been shown; for instance there are seven  stations in Benin and 44 in South Africa. There may also be other countries whose installed or planned stations may not have been counted due to a lack of coordination of efforts and information.

The installation of such equipment will no doubt be of benefit to AFREF, and the AFREF stations will be of benefit to the other projects. If all groups currently active with the installation of GNSS equipment in Africa could coordinate and collocate such installation with other instrumentation such and seismographs, ionosondes, tide gauges and meteorological equipment, the limited resources available for such installations could be used to increase the overall coverage of permanent GNSS reference stations for the benefit of all groups.

[image: image3.png]GPS, GLONASS, SLR,
= )

~ m— 1





Figure 2: GPS, GLONASS, SLR, VLBI, and DORIS Sites in Africa

So far, ISCA has developed guidelines for permanent reference stations based on the IGS standards and organized several technical and capacity building workshops, including a two-week training on GNSS data processing held in Nairobi in 2007.

Planned Activities

As shown by the above discussion, the AFREF project is ongoing. However the operations so far could be regarded as a demonstration phase showing the installation, operation, data dissemination and analysis capabilities. This demonstration phase was designed to end in 2007, and the project has now moved into the implementation phase. The activities to be undertaken in this phase are as follows:

1. Organize Regular Management Meetings of the Steering Committee. The Steering Committee has conducted their work mainly through electronic communication and occasional, opportunistic side meetings during workshops and geoinformation events. Though electronic exchanges have been found to be very useful and almost indispensable, there are issues that cannot be dealt with conclusively though virtual meetings and communication. The side meetings have also been useful, but most of the time, only few members of the Committee would be present at any one event, making it difficult also to deal conclusively with issues. The result has been a backlog of pending decisions to be made. For effective coordination of the project, regular in-person meetings of the steering committee are required – say, semi-annually. For maximum effectiveness, it would is also proposed that a dedicated AFREF network coordinator should be engaged to oversee the activities of the day-to-day operations of AFREF. 

2. Organize Experts’ Implementation Symposium. Though several technical workshops have been organized by the Steering Committee, a focussed implementation symposium of the experts and implementers is now necessary. The participants should include all the stakeholders and experts from Africa and outside, as well as the national officials with the mandate to maintain the geodetic infrastructure of the countries, and African universities involved in teaching and research in geodesy and other allied disciplines. The outcome of the symposium should include a definitive map and inventory of all existing GNSS stations and other geodetic infrastructure in Africa, showing their current operational status vis-à-vis suitability for the AFREF initiative; final definitive map of the optimum locations of the first phase of the network stations and gaps; and the parameters of the best-fitting datum for the African Terrestrial Reference Frame, including the appropriate epoch for the first computation (say 2009) and vendor-independent equipment specifications for standardisation purposes.

3. Organize Policy Makers’ Workshops. The technical workshops organized by steering committee have so far been targeted at professionals who are expected to participate in the establishment of the stations or computing of the data products. While this has reinforced the existing capacity for the technical implementation of the project, the policy makers who would make the ultimate decision to fund the project have not yet been addressed. An awareness campaign directed at this level of policy makers is required to secure the necessary political and financial support for the project.

4. Identify On-Going GNSS Projects. At the time of preparing the Windhoek Declaration, it was expected that national authorities would object to foreign organizations installing and maintaining GNSS stations in their sovereign territories. As the GNSS technology permeates the society, initial security worries have been allayed and countries have allowed several foreign entities to maintain GNSS installations for various scientific purposes. These include the International Heliophysical Year/Scintillation Network Decision Aid (SCINDA), the International Research Group in Geophysics: Europe – Africa (GIRGEA), the African Monsoon Multidisciplinary Analysis (AMMA) and Millennium Challenge Account (MCA) projects. It is expected that the positioning and data reporting needs of some of these projects would be similar to those of the AFREF project, or if not, that the marginal effort to make them compatible would be small. Identifying these projects will enable an agreement to be reached with them to share resources.

5. Develop Data Contribution and Dissemination Policy. An important aspect of the AFREF project is making the raw data from the stations available to the designated computing centres, and thereafter making the data products available to the community of users. A data sharing policy is necessary to spell out the type and standards of data required from the stations, the conditions for a station to contribute its data to the computing centre and how the data will be processed and disseminated to users. This will help reduce if not remove lingering reluctance to contribute data to the continental effort.

6. Develop Full Participation Protocol. Given the national implementation/maintenance model, a protocol should be developed for countries, organizations and projects to have their stations included in the AFREF network of stations. Such a charter will include specifications for the receivers and antennae, physical environment, data content and supply frequency, and minimum length of operation of the station, among others. The protocol should provide for different levels of participation, from maintenance of station and supply of data, through to complete computation and data dissemination. So far, RCMRD and HartRAO have been identified as two potential computing and data centres based on their facilities and experience. Once this charter is finalized, a Memorandum of Understanding (MoU) would need to be signed between ECA and these facilities, as well as with others currently involved in different aspects of the AFREF project, to formalize and spell out their various roles.

7. Convene Partners Forum. It has already been recognized in the Windhoek Declaration that countries may require assistance to install and/or manage the stations. To give impetus to the implementation, a Partners’ Forum should be organized to bring together the potential contributors and beneficiaries of the assistance. 

8. Compute Transformation Parameters. Once the first computation of the datum has been completed, parameters would need to be computed for transforming new GNSS observations and other geoinformation products to the new system. The parameters will need to be computed for all the national reference frames currently in use. Before this can happen, National Mapping Organizations (NMO’s) will have to carry out short term GNSS campaigns to occupy points whose coordinates are known in the existing National reference frame or frames. The NMO’s will be totally responsible for the processing and computation of such campaigns to be used within their jurisdictions for the estimation of transformation parameters to an ITRF reference frame.  Emphasis in this activity for the AFREF project will therefore be on developing the methodology and continental standards and building the capacity to undertake such campaigns and to estimate transformation parameters and their use, with progress being reported through appropriate intergovernmental bodies.  

Methodology, Timing and Cost Estimate for 2008 – 2009 Biennium

	Activity and Timing
	Methodology and Timing
	Cost Estimates

	1. Steering Committee Meetings

· On-going
	· Appoint AFREF network coordinator and small network management committee (2-3 persons)

· Agree on frequency and timing of meetings.

· Send notices and reminders 

· Service meetings and document outcome
	· Travel and DSA for 10 participants for four meetings (two each in 2008 and 2009)
$120,000
· Two years salary for the AFREF network coordinator @ $1,000/month
$24,000

	2. Implementation Symposium

· Preparation: Quarter 1, 2008;

· Symposium: Qtr 2, 2008
	· Engage a consultant to prepare a research paper, with recommendations on the issues to be decided on. 

· Prepare a task brief with details of the objectives of the symposium. 

· Network management committee to prepare vendor-independent specifications and CORS implementation guide (as input document for the symposium)

· Distribute widely and call for abstracts.

· Organize symposium and document agreed parameters.
	· 4 work-month category B consultant @ $7000/month
$28,000
· Travel and DSA for 53 national geodetic officials, average $3000 each
$159,000
· 20 Scientists and experts from universities and other research institutions @ $3000 each
$60,000
· Interpretation and translation
$50,000

	3. Policy Makers’ Workshops

· Whole of 2008
	· Prepare not-more-than-five-page information booklet for policy makers.

· Liaise with African Union Division of Science and Technology to include an agenda item on AFREF presentation in meeting of Bureau of AMCOST.

· 2 Workshops for national officials that the Heads of NMOs report to – one Anglophone, one francophone. 
	· Printing of 500 copies of booklet
$5,000
· Travel & DSA for two experts or staff to attend two meetings 
$12,000
· Travel & DSA for 53 national participants from member States
$159,000

	4. On-Going GNSS Projects

· Qtr 2, 2008
	· Prepare and disseminate a data collection form.

· Follow up with phone calls.

· Organized coordination meeting with heads of identified projects.
	· Postage and communication costs
$5,000
· Travel & DSA for 10 participants
$30,000

	5. Data Policy

· Qtr 1 – 2, 2008
	· Review data policy from similar continental reference frame projects.

· Draft policy/protocol and validate at meeting of Steering Committee

· Disseminate document
	· Staff time 

	6. Participation Protocol

· Qtr 1 – 2, 2008
	· 
	· 

	7. Partners’ Forum

· Qtr 3, 2008 and Qtr 1, 2009.
	· Prepare task brief and disseminate to potential partners.

· Follow up with phone calls.

· Invite national officials of potential beneficiary countries.

· Invite African experts.

· Document agreements and follow up on delivery of pledged support.
	· 2 x Travel and DSA for about 10 national officials @ $3000 each
$60,000
· 2 x Travel and DSA for about 5 experts @ $3000 each
$30,000

	8. Transformation Parameters

· Qtr 4 2009
	· Prepare and disseminate booklet 

· Organize validation workshop
	· Travel & DSA for 53 national participants from member States
$159,000

	Grand Total (2008-2009):
$1,001,000]


Role of ECA

The installation and continuous maintenance of at least one CORS facility in each African country requires the active participation of the national authorities responsible for mapping and geological/geophysical surveys. Though individual stations will be funded and maintained by individual countries, the national offices need to be involved on a collective basis due to the need for consensus on several issues discussed above. This group involvement is best realized through an established forum of the national offices and other stakeholders, as is supported by examples from other continents: 

· The European Reference Frame (EUREF) is maintained in close cooperation with EuroGeographic – organisation of the European National Mapping and Cadastral Agencies (NMCA).
· The South American Geocentric Datum (SIRGAS – Sistema de Referencia Geocéntrico para Las Américas) was defined and is being maintained in close cooperation with the Pan-American Institute of Geography and History (PAIGH). 

There is no such pan-African institute or organization through which national mapping authorities can undertake such collective activity. The only forum that brings together heads of geoinformation offices (mapping, remote sensing, cartography, spatial data infrastructures, etc) is the Committee on Development Information, Subcommittee on Geoinformation (CODI-Geo, now CODIST-Geo). CODIST is the inter-governmental body that oversees and advises on ECA’s programme on harnessing information for development, which meets every two years.

The subcommittee on geoinformation subsumes the functions of the old United Nations Regional Cartographic Conference for Africa, and also fulfils the role of Permanent Committees on Spatial Data Infrastructures that exist in other regions. It provides a forum for designated officials to meet and share lessons and ideas with one another. It also has the legislative function of proposing and adopting guidelines to harmonize practice in Africa. CODIST-Geo has working groups that deal with focussed areas of their work, one of which is the AFREF Working Group, which has been expanded into the AFREF Steering Committee as discussed above. 

CODIST-Geo is not a legal body or substantive entity and therefore cannot enter into agreements. As such, correspondences regarding AFREF issues are usually sent on behalf of the Steering Committee either by RCMRD as the Secretariat of AFREF, or by ECA’s Geo-information Systems Section as the overall secretariat of CODIST-Geo. Legal agreements and memoranda of understanding are also signed with ECA. The work programme of ECA for the 2008-2009 biennium includes a field project activity on AFREF, and as such more time and resources can now be devoted to the AFREF project than in past years. For example, until a decision is reached and resources allocated for the proposed AFREF Network Coordinator, ECA will assign will assign one of the GIS Assistants to dedicate 50% of her time on AFREF coordination. Eventually, when the Coordinator position is established, ECA will provide office space and administrative support to the post.

Potential Role of NEPAD and the African Union 

The New Partnership for Africa’s Development (NEPAD) is an economic development programme of the African Union, which sets out the principles and priority areas for Africa’s development. Many of the programmes of NEPAD and the African Union cannot be undertaken without adequate maps and other geoinformation products. As already established, these geoinformation products need to be based on a uniform geodetic reference frame. AFREF, as a project to create this geodetic foundation should therefore be aligned with the NEPAD objectives and priorities. Since the bulk of the work in establishing a geodetic datum and the associated reference frame derives from the physics and mathematics of the earth, AFREF should therefore be aligned to NEPAD’s programme on science and technology, as contained in the “Science and Technology Consolidated Action Plan,” particularly Programme Cluster 4 on “Information and Communication Technologies, and Space Science and Technologies.” One of the indicative activities under Programme 4.2 on “Establishing the African Institute of Space Science” is the “establishment of an inter-governmental experts’ committee.” However, the particular inter-governmental committee envisaged there is one that will conduct a feasibility study for the establishment of the African Institute of Space Science. Further discussion is therefore necessary with the AU’s Division of Science and Technology on how CODIST-Geo, as an inter-governmental experts’ committee, and its working group on AFREF should channel their work into the ministerial structures of the African Union, notably the African Ministerial Council on Science and Technology (AMCOST). 

Expected Outcomes

1. Formalized Coordinating Arrangements. A revamped or restructured management structured having regular meetings. Still under the auspices of CODIST-Geo, but with additional reporting to the appropriate AU structures.
2. Operational Participation Protocol. A protocol detailing levels of participation would have been adopted and signed by participating member States and other organisations and institutions. The protocol should include data sharing/contribution agreements, site maintenance responsibilities and data processing, archiving and information dissemination.
3. Network of Permanent GNSS reference Stations. The reference frame will be realized by a network of permanent GNSS reference stations maintained by NMOs and other organisations and projects, who have signed the AFREF Operational Participating Protocol. Such stations will serve as reference stations for further network densification and short-term GNSS campaigns.  A user everywhere in Africa should be not more than 1000Km from one such point, with at least one in every country.4. An African Continental Reference Frame. A uniform reference frame based on the International Terrestrial Reference Frame (ITRF) realized through observations derived from the network of permanent GNSS reference stations. 

4. Awareness among policy makers. Policy makers responsible for science and technology, surveying and mapping, infrastructure development and other related fields will be made aware of the importance and role of the reference frame in their sectors so that they will support the relevant national activities, both politically and financially.
5. Skills development and capacity building. Technical staff to be involved in the installation and maintenance of the reference stations will be trained and equipped with appropriate knowledge, skills and expertise to undertake necessary activities.
6. Partnerships. Partnerships will be developed with other projects and initiatives that are installing GNSS and other observational equipment to pool and share resources, data and information.
Funding Issues

ECA has the general mandate to support geoinformation activities in Africa, and has been working on AFREF project as an extension of its work on spatial data infrastructures because the geodetic reference frame provides the basis for geo-referencing of all services and development activities. Now AFREF has been programmed explicitly, but as a field project. As such, it is not budgeted for in the regular budget. Extra-budgetary resources are therefore being requested to fund the implementation phase that the project has moved into. 

_943789290.doc



